Salt Lake City @ University of Utah

# Convention Chair and Lo-Chair for SLC Meeting

Attendees: 	Beth Witt, Convention Chair					Mark Algren

Mary Ann Christenson, TESOL President for 2002		Tom Riedmiller

Jeanne Lachcowski, Local Co-Chair				Noella Kim

Dean Huber, Local Co-Chair

Jim Bame, Secretary

MINUTES:

- Need to get corporate support team leader in place as soon as possible to get letters out

1.	Teams updates from each core planner

- Jeanne Lachcowski

  - some teams on hold because of the Olympics

  - Volunteers not registered for conference will get a visitor pass to the exhibitor’s hall

- Dean Huber

  - Special deal with Snowbird (ski resort); link on web for sign-up

  - Community Outreach new team this year; working with a lot of businesses with ESL employees; needs to be expanded to do more with adult community schools; gray area with Promotion team

  - Corporate Support an issue because budgeting begins in November; in public education, seeing budget cutbacks from State funded institutions

- MAC (Mary Ann Christenson)

  - Need hotel rooms to offer to team leaders who need them (40 people)

- Beth Witt

  - All is well

- Bill Eggington

  - Met with members of school boards and distributed information

  - Downloaded from the web K-12 sessions and made sales pitch to attend and also pitch as professional development; enthusiastic but budget tight

  - Bag distribution: Someone there at all times to lift heavy boxes; Conferon can do?

  - Educational Visits:

2.	Convention Program, Scheduling, & Preparation

- Program book is closed via Helen Kornblum; had 6 people proofread

- Received January 8 and had to return by the 14th; quick turnaround; We should expect 2003 program edit in December

- Even those who are introducing and giving awards at plenaries need to be decided early on to go into the program book

- Now online at TESOL website; Brandy at TESOL Office has service on web where you can make a customized convention schedule

- TESOL Program book is shorter now; maps of hotel and convention center are out; they will be in the Convention Planner and there will also be a colored handout

- Jaime Hitchcock’s Convention Report (on lime green paper)

- HOUSING IS GOING QUICKLY (Marriott is gone!!!)

- $65K so far in sponsorships

- Conferon’s responsibility is Conference troubleshooter; service areas such as messaging; liaison with A/V folks; need them to be “runners?”

- March meeting on 15 and 16 @ Marriott to walk through the convention center

- June 1 debriefing meeting when SLC team leader reports will be due

3.	Core Planner communication during the convention

- Planning to meet each morning at 7:00 during the conference in the TLC room (not on Thursday); TLC Room will be Communication Central and Troubleshooting dispatcher; TLC room is place for breakfast & lunch, for all team leaders, war room

- TLC Room is Convention Center 253A (near business center, towards the back, where deaf interpreters will also be) Press will be in checkerboard room (secret room not on the maps); bulletin boards for messages and pictures of all the team leaders

- SECRETARY: need to be a morning-bird because they have to be at each meeting before, during, and after the convention

- Leaders will have identifying ribbons (team leaders in specific color), walkie-talkies, and pins “Ask me—I can help”

- Open for Baltimore chairs in SLC

4. 	Core Planner Convention Responsibilities

- Big job between now and April is recruiting volunteers and market (maybe dip into Olympic volunteer bank of those who did not get to volunteer this time around)

- Link on TESOL website for convention volunteers instead of recreating each year (Diane may be talking to people about that)

- Opening plenary, 7-9 pm, Tuesday night of the convention is a good time to all come together

- Featured speakers: one core planner should be at each of the plenaries to represent

- During convention, try to check in with team leaders several times

- Exhibit Hall is fairly open because we want people to go through and buy stuff!

- Team leaders are welcome to come to the 7:00 am morning meetings

- SLC registration begins Monday 3-6 pm, educational visits start at 11:00 am

- Support Intermountain TESOL presenters (I-TESOL = 300 members)

- Spotlight Sessions are Chair invited sessions (don’t have to go through adjudication process to present)

5.	“Punch List” before the next meeting

- Team Leader gifts: something wooden and crafty

- (for Baltimore, Appalachian Mountain business card holder)

- During Convention, take around a piece of paper to jot down positives and negatives as you go around the conference; doesn’t have to be under your field

- Important to find places to sit “networking stations” near food or coffee stations

- 2 food stations in the exhibit hall and at least 4 coffee stations throughout the Convention center

- Requesting signs: need to fill out form and give to Jaime (22x28 in. and standard font) which are separate from event signs.  Particular to teams

- Not sure if there is a standardized sign?  Go ahead and order and have Jaime identify if it is a duplicate.  Due February 5 for SLC, probably in January for us

- Note: Number signs for tables, general arrow signs, restroom signs?

- We will get a list of what signs SLC needed and what worked and what didn’t

- TESOL by NIGHT tickets $30 for SLC; Thursday, 7:00-10:00 at Mormon Tabernacle

- Baltimore TESOL by Night: Baltimore Symphony Orchestra? Baltimore Museum Art? Peabody Library? Ft. McHenry? Inner Harbor cruise?  Aquarium in 1994 was too cramped

- During tomorrow’s 1-minute reports, Jim will send via email to everyone

- During introductions: We should share what we are responsible for so that team leaders can think about important things to share (so we can talk over lunch)

- I need to know timeline; look over booklet and descriptions before tomorrow!

Salt Lake City @ University of Utah

# SLC and Baltimore Core Planners + SLC Team Leaders

Attendees: 	SLC Core Planners and Team Leaders

Baltimore Core Planner

My Teams and SLC Team Leaders:

- Bag and Program Distribution: Cindy Hallen & Joe Leishman

- Convention Information: Diane Ogden

- Corporate Support: Milton Witt (w/ WATESOL)

- Interpreters Service for Hearing Impaired:  Dee Gardner & Rebeka Harnois

- Secretary: Jim Bame

Myles’ Teams:

- Alternative Housing

- Hospitality & TESOL by Night

- Media Publicity (w/ WATESOL)

- Volunteers & Employment Clearinghouse (w/ WATESOL)

- Promotion & K-12 Liason (w/ WATESOL)

- Educational Visits (w/ WATESOL)

MINUTES:

- Where are we in the Convention Process?

  - Handbook is closed; edits of changes sent to Helen Kornblum and she put into one master copy

  - Team Leader dinner on Friday of convention week

- Signage:

  - need a large one of the entire Convention Center on foam core (maybe laminated or something to be able to write on and indicate changes, highlights, etc.)

  - Signs and list of signs requested to be passed on to Baltimore

- BIG JOB – RECRUIT

  - from now to April, carry around a preliminary program and give them to everyone and anyone who is interested

  - Great way to recruit is to talk to principals of schools and get them to recruit people from their schools to attend; stress growth in school of ESL and need for education and training (ESL and content area teachers)

  - Another idea for recruiting: to ESL students in IEP’s, Community College programs, etc. in the area to come and go to the exhibit hall? Attend sessions?

  - Baltimore recruit for SLC take some postcards and preliminary programs to start recruiting for volunteers to man the table

  - Idea for educational visits—include teacher training programs at UMBC, CND, UMCP

- One Minute Team Leaders Reports

- 2 goals: (1) Share information by hearing it and reading via email and (2) make connections with people that might be on different teams (stay away from narrative; speak in bullet points)

  - Kathy McEntire: Academic Credit; contacting local universities to find out who can give short credits and public school inservice credit; in preliminary program and web

  - Monica and Tom: Advocacy; solidified Alicia Swazo for Tuesday evening opening plenary to receive award for husband, signed up volunteers to work advocacy booth; advocacy issues-lots of them and changing, have to see what they will be closer to April; booth will be in registration area

  - George and Heidi: Awards and Raffle; 25 prizes collected and need 150; something from MDTESOL; booth will be near exhibit booth where there’s high traffic

  - Cyndi and Joe: Bag & Program Distribution; organizing volunteers; need 18 and have 12 currently; hoping volunteers will not have to lift heavy boxes and ok to bring boxcutters; will have handtrucks and dollies???

  - Marios: Community Outreach; found group of people who are experts in work ESL; 1 hour on Saturday afternoon; inviting business represents; will be happy with 40 people in attendance; contact at State level with Workforce service department; helpful with identifying companies; invitations are going out first week of February; involving local business community is new and strongly supported by Central Office

  - Diane Ogden; Convention Information; have lots of questions and will be sending around gray notes to team leaders to answer questions to help her compile a FAQ sheet to give to volunteers; needs to get a conference book beforehand (page numbers not on web); has a sheet of FAQs from the past; didn’t know sessions were in Marriott too; need layout and setups there

  - Sherry and Yvonne: Educational Visits; have gone to all of the schools and met with folks; excited to be participating; in continual contact with them regarding directions, escort to be provided from school (decreases volunteer needed), transportation to and from, signs for bus loading areas; schools want to know registration numbers in March (pg. 26 in preliminary program); needs volunteers at booth on MONDAY morning before conference begins; first visit at 11:00 to give time for set-up

  - Judy and Liz: Employment Clearinghouse; actively recruiting volunteers; 21 firm volunteers which is 1/10 of needed; running up against K-12 teachers whose principals are not giving time off and are not offering to pay; Tom and Mark did last year at St. Louis

  - Beth: Energy Breaks; listed on web and in prelim program (pg .24) 12 roundtables and a TESOL leader to discuss a topic over granola bars

  - Karen: Global Village Hospitality; waiting for affiliates list; compiling list of favorite international students’ handout via questionnaire to folks

  - Lynn: Graduate Student Forum; putting together final program; have all volunteers; mini-conference 4 hours of sessions; 1 hour plenary; and lunch on Tuesday; next week is the registration deadline (is separate, but free) and can be downloaded of web; linked on TESOL; needs interpreter services???  Is there a box on registration form for graduate forum if the need and interpreter???

  - Jim: PhD Student Forum; 12 students and just as many interest section; informal networking event; Wed. night

  - Donna, Margot, & Tim: Hospitality; Final list of services can be downloaded from web (can reduce printing); donate 1 ream from each institution; suggested restaurants; optimistic about excursions/tours; not responsibility for lost and found; security is responsible; in bag want to put as a long, skinny card that’s double-sided with final list (same as web list); list of places that can host parties and receptions

  - Rebeka: Interpreting Services; drafted contract for Jaime to look at first and give to interpreters to sign; all interpreters in line; need to compile list of participants who need interpreter and start scheduling; concerned about having interpreters having longer than 8 hour days, what services & conveniences are available for them?; need a room for the interpreters and designated seating

  - Lonnie & Kate: Media & Publicity; putting together press information; providing room for them; trying to anticipate needs; trying to provide digital and hard copy information (ie: plenary speaker pictures and of local leaders); people in affiliate with a journalism background to volunteer (contacts); mayor can’t come, but trying to get governor; moved deadline for first contact visits/first information because Olympics; need help to identify folks who can be spokespersons for various sections; media will be interested in certain topics and stories; trying to stay ahead of what the issues are

  - Ann: Networking; Hot Topics will be posted outside networking room; informal posting; Carolie Erickson is rep for AFT to talk with collective bargaining and EFL; Miami teacher to talk about his experience (union stuff??) Rep from State Department to talk about teaching abroad for the government; Sept 11 topic after their spotlight presentation (NOTE: Hard to be topical at conference because call for papers due 1 year before so these networking groups are good because you can be topical as well as spotlight sessions because don’t need to go through adjudication process)

  - Lydia: First-Timers session & Poster Session; Tuesday and Wednesday; scavenger hunt through the program book; Poster Session in lobby outside the electronic village Wednesday-Friday

  - Randy: Presentation Facilitators; volunteers that ensure that presenter is there and keep track of attendees to see what is interest for next conference use; NOT moderators; breaking chunks of morning and afternoons; need 30-40 volunteers; meal tickets will be discussed in mid-March for minimum of 4 hours of volunteer time that is good only in the convention center; in the past, a checklist broken down by sections of the convention center to check off; have Convention Center floor plans and need Marriott floor plans.

  - MAC: Pre and Post Convention Institutes; under control and have volunteers though not as many as needed.

  - Brent: All Idaho schools have received information and NGO’s and IEPs

  - MAC: Protocol & Opening Plenary: scrambling

  - Holly: Exhibitor’s Assistants; sit in a booth for a publisher while they take a break and run errands; only 2 publishers have requested assistants; have 3 volunteers; needs a co-chair with a cell phone! Booth will be right inside the exhibit hall; last year, needed about 12 volunteers; publishers have expressed interest in donating free dinners and books, etc. for the volunteers

  - Linore (Oklahoma): Strands; communicating with interest section leaders to help identify a desired strand to make use of time during the convention

  - Emily: TESOL-by-NIGHT; working on details and literature; how big is the dance floor, how many tables, etc. (NOTES: Curtis Isaak put together ESL choir representing 25 countries)

  - Diane: Treasurer; have checks so need receipts that have been okayed by the local co-chair; keep copy for yourself; local co-chair has budgets

  - Hannah: Features speakers; have information and gifts are here, working on hotel

  - Diane S-K: Volunteers; divided duties, pre-conference=collect information on volunteers, prelim contact; on-site conference (Curtis); getting names in through the internet volunteer form (have 70 so far); have indicated areas they’re interested-have been recruited in the meantime for other teams; need to work together for the same information; team leaders need to send list of their volunteers; Diane will forward names that have listed interest in particular teams to the team leader; will email to say that team leader will be contacting them; We need to get our volunteer website up and running soon; about 400 volunteers and about half are for Employment Clearinghouse; if volunteer is not registered in conference, they can get a meal voucher if volunteering for 4 hours and a free exhibit pass; good for literacy ESL folks who need to know about materials; need to send Jaime Hitchcock list of those people a month before the conference; discussion about volunteer check-in

- Brief Core Planner Reports

Bill Eggington:

- concerned about attendance of local K-12 teachers; need to attach at the board level and get superintendent support

- Will send out a volunteer policy sheet on how to respond to volunteers

- Should I be doing any special during the convention?

- 	Attend the opening plenary (can bring friends/family; open, don’t need a ticket)``

- 	Stop by the TLC room occasionally

  - Communicate with core planners

  - Touch base with volunteers

  - Distribute meal vouchers

  - Attend team leader party

  - Take notes

7.	Final Meeting: Saturday, March 16

- will walk through the Salt Palace

- need to find out about where volunteers can park

Salt Lake City @ Marriott Lobby

# Baltimore Core Planners

Attendees: 	All Baltimore Core (Mark, Tom, Brenda, Joan, Myles, Noella)

Agenda:

- Poster Brainstorm

- SLC Booth

- Shadowing Funds

- Team Assignments

Plenary Speakers

Minutes:

We are basically on-schedule for the conference timeline!

- Poster: Poster/Flyer that goes out to a fairly limited area (i.e: East Coast, MATESOL programs)

- 1,400-1,500 to print

- like St. Louis and New York or postcard like Salt Lake City

- different use of logo in different

- need to list all the features of the convention?

- Contact information has to go on—don’t want to get too crowded

- Better off using direct marketing using the postcard format?

- For St. Louis: Had postcards ready at Vancouver booth and those interested in attending filled out a postcard that was later sent to them; builds a mailing list

- Need to get email addresses

- Had free giveaways, but you had to sign up first

- What do we want to put into the poster? Logo should be prominent

- Who is our audience? People who don’t need to be attracted to the location?

- The simpler the better

- Cubes, boxes, 3-D telescoping squares, painting

- Postcard: logo in the middle with quadrants

- Box with TESOL 2003 logo on front with the opportunities you can find at the convention coming out of it

- T-Shirts available for Salt Lake City  that have our logo on it.  They can’t take it, but they can wear it while they are working the booth; to sell, local affiliates could order and sell

- Plenary & Featured Speakers: Our preferences; will we be able to preview talk?

- Laura Bush for opening if we can b/c it would be a good draw; need to know what their administrations view is on ESL and bilingual education; risk of last minute cancellation for any politician; would be exciting for anyone

- Jodi Crandall as back-up for L. Bush for opening (if she doesn’t speak, Eric Dwyer from Florida will have to promise to have her as a featured speaker in 2004); would also like to have her not just as a back-up, but as a scheduled featured speaker

- Myles: Jonathon Kozil, author of “Savage Inequality” ( Tom agrees, because he is educational, but it would be a dark mood afterwards

- Purpose of the opening plenary is to get people excited for the week ahead and speak to the theme

- Dr. Raouf Mama – storyteller speaks to theme of “Hearing Every Voice” and an international speakers

- Bill Bryson – author of “Lost Continent,” humorous or David Sedaris

- Sandra Cisneros – “House on Mango Street,” required high school street and used in ESL

- Amy Tan as a featured speaker

- A student voice a night as a featured speakers: Start scouting around to find student who could speak of their experience

- Joan will look into a student theatre group

- Ongoing video at entrance of TESOL lobby with clips of students and teachers related to “Hearing Every Voice”

- PBS show on the “Immigrant Experience”

- Advocacy: Featured speakers that could speak on overview of advocacy issues throughout the globe both for students and problems that teachers are having

- EACH speaker has to have a focus of teachers teaching ESL, not a political issue.  Has to be appropriate to the audience and the setting

- U. of N. Iowa - Dr. Mark Ray; studied Postville, IO about Hassidic Jews who bought a butcher factory and brought in migrants; Cross-cultural experience.  As a featured speaker because a little dry.  Probably would be cheap.

- Edward Stewart at UMBC? Sociologist who speaks on cross-cultural communications; try to look around

4. 	Calendar for next meeting with Core Planners and all Team Leaders

- Need to meet in April in Baltimore after SLC at the Convention Center on a Saturday

- With us getting together in the afternoon before at a restaurant in the middle

- March 29 & 30 Option 1 (Good Friday)

- March 8 & 9 Option 2

- April 19 & 20 Option 3 (right after convention)

5.	Shadowing Funds

- Designated shadows for those who cannot attend conference

- Which teams need to shadow in SLC?

  - Promotion (need to find out where money comes from)

  - Convention Information

  - SWAP Shop

  - Volunteers (2)

  - Educational Visits (2) Heidi Platt, Jill Bayse-Featherston

  - Energy Breaks

  - Hospitality

  - Secretary

  - Community Outreach (?)

  - Strands (give Linore a little money to come in an extra day for meeting; money from where?)

- Need to find out who already has institutional support, who has partial support?

- Need to find out if there are 10 rooms that are blocked off for the 2003 team?

- Local co-chairs are allowed to TLC room for breakfast and lunch, we would only have dinner

- I’ve been in meetings since 10:00 this morning and it is now 7:00 pm.  That’s 9 hours!